## Burndown List
# | HT Date: | 2019-04-12 |  |  | Days in Month: | 29 | Status | 2019-04-07 | Comments | #
| Task | Lead Time (months) | NLT | RI | AKC | Target Date |  | NLT Date
1 | Establish goals for HT (profit/service/preparation/etc.) | 6 | 0 | BOD | NA | 2018-10-20 | C | 2018-10-20 | Normal Double 90 Dog Master, Double Senior, Double Junior | 0
2 | Identify HT committee members | 6 | 0 | BOD | 12 | 2018-10-20 | C | 2018-10-20 | Chairman: Eric Whitacre Co-Chairman: Brian Garman Secretary: Leslie Stanley Co-Secretary: Head Marshal: Jeff Sparrow Co-Head Marshal: Rita Bumgardner Bird Steward: Tommy Baker Hospitality: Megan Meadows | 0
3 | Reserve/acquire test date | 6 | 0 | Sec | NA | 2018-10-20 | C | 2018-10-20 | 4/12-14 - Easter 4/21 | 0
4 | Reserve/acquire test grounds | 6 | 0 | Chair | 6-12 | 2018-10-20 | C | 2018-10-20 |  | 1
5 | Identify stakes/dog limits/flyers/etc | 6 | 0 | Chair | NA | 2018-10-20 | C | 2018-10-20 |  | 1
6 | Pull together and list in order judge candidates | 6 | 0 | Chair | NA | 2018-10-20 | C | 2018-10-20 |  | 2
7 | Order birds | 6 | 2 | Chair | 6-12 | 2018-10-20 | C | 2018-12-17 | 12/30 - Need to figure bird count 1/3 - Tommy is going to tell Ed we need ~450 1/27 - Tommy talked w/ Ed and we are setup for 450 | 3
8 | Solicit judges | 5 | 1 | Chair | 12 | 2018-11-18 | C | 2018-12-17 | 12/30 - Need one more Jr/Sr judge | 2
9 | Start Soliciting volunteers | 4 | 0 | Head | NA | 2018-12-17 | C | 2018-12-17 | 1/13 - Email sent | 2
10 | Arrange accomodations for judges/workers/etc | 4 | 0 | Chair | NA | 2018-12-17 | C | 2018-12-17 | 1/6 - Made at Quality Inn in Culpepper | 4
11 | Register event w/ AKC | 4 | 0 | Sec | 4 | 2018-12-17 | C | 2018-12-17 |  | 2
12 | Lineup paid workers | 4 | 0 | Head | NA | 2018-12-17 | C | 2018-12-17 | 12/30 - PWC 4-H have been given the date and are in | 2
13 | Lineup food services if applicable | 4 | 1 | Chair | NA | 2018-12-17 | C | 2019-01-15 | 1/2 - Leslie talked w/ Milton and he is in | 10
14 | Create Event on EE | 4 | 1 | Sec | NA | 2018-12-17 | C | 2019-01-15 |  | 2
15 | Inventory consumables (Ammo, poppers, ribbons, etc) | 3 | 0 | Equip | NA | 2019-01-15 | C | 2019-01-15 | 2/4 - Title Coins 47 (good) Ammo 11 cases - 5 at Eric's (good) Poppers 3 cases - Edwin has 10 we need to purchase (good) | 4
16 | Order Ribbons | 4 | 1 | Sec | 4 | 2018-12-17 | C | 2019-01-15 | 2/4 Ribbons - M 99, S 52, J 81 - Need to order enough for Oct - M 75, S 50, J 90 Ribbons ordered | 4
17 | Lineup flyer shooters | 3 | 1 | Gun | NA | 2019-01-15 | C | 2019-02-13 |  | 4
18 | Mail Premium To AKC | 2 | 0 | Sec | 1-1.5 | 2019-02-13 | C | 2019-02-13 | Approved 2/26 | 5
19 | Identify and order judges gifts | 2 | 1 | Chair | NA | 2019-02-13 | C | 2019-03-14 | 2/4 - Have YETI coolers | 5
20 | Order necessary consumables (Ammo/Poppers) | 2 | 1 | Equip | NA | 2019-02-13 | C | 2019-03-14 | Ammo and poppers in posession | 4
21 | Finalize Test on EE | 2 | 0 | Chair | NA | 2019-02-13 | C | 2019-02-13 | Approved 2/26 | 4
22 | Ensure equipment is available and in working order (wingers/blinds/popper stands/gun stands/mule) | 2 | 1 | Equip | NA | 2019-02-13 | C | 2019-03-14 | 2/25 - Training day | 5
23 | Get Permit from DGIF | 2 | 1 | Sec | NA | 2019-02-13 | C | 2019-03-14 | 2/21 - Permit mailed…will be mailed out on 3/19 | 5
24 | Make reservations for judges/setup dinner | 1 | 0.5 | Chair | NA | 2019-03-14 | C | 2019-03-28 12:00 | 4/4 - Leslie called Grioli's and made reservations for Thurs/Fri | 4
25 | Make arrangements for portable toilets | 1 | 0.5 | Chair | NA | 2019-03-14 | C | 2019-03-28 12:00 | 4/2 Ordered 3 - 1 at silo, 1 at ponds, 1 trailer | 5
26 | Make arrangements for lunches | 1 | 0.5 | Hosp | NA | 2019-03-14 | C | 2019-03-28 12:00 | 4/4 Leslie called Milton and gave count for Fr/S/S | 5
27 | Finalize Running Order | 0.75 | 0.5 | Head | NA | 2019-03-21 06:00 | C | 2019-04-04 18:00 | 4/2 Complete | 8
28 | Email to judges w/ presentation | 0.5 | 0.25 | Head | NA | 2019-03-28 12:00 | C | 2019-04-04 18:00 | 4/4 - Complete
29 | Email to paid workers w/ presentation | 0.5 | 0.25 | Head | NA | 2019-03-28 12:00 | C | 2019-04-04 18:00 | 4/4 - Complete
30 | Pull together blind/line buckets | 0.5 | 0.25 | Head | NA | 2019-03-28 12:00 | O | 2019-04-04 18:00 |  | 6
31 | Finalize workers | 0.5 | 0.25 | Head | NA | 2019-03-28 12:00 | O | 2019-04-04 18:00 |  | 6
32 | Sundries Tubs | 0.5 | 0.25 | Hosp | NA | 2019-03-28 12:00 | O | 2019-04-04 18:00 |  | 7
33 | Train paid workers | 0.5 | 0.25 | Head | NA | 2019-03-28 12:00 | O | 2019-04-04 18:00 |  | 7
34 | Train flyer shooters | 0.5 | 0.25 | Gun | NA | 2019-03-28 12:00 | O | 2019-04-04 18:00 |  | 7
Receive Birds
Kill Birds
Setup w/ Judges
Notes:
Date/time to open test
Date to close entries
Thursday Help/Judges meal
Application from DIGF
Discuss with other presidents (Mid Atl, BBKI, Tidewater) about mutual help for hunt tests.
Formulas:
Target Date = C1-([Lead Time (months)]*G1)
NLT Date = C1-(([Lead Time (months)]*G1)-([NLT]*G1))

## Sheet3
Count | % Pass | April | October | Total | Needed | Buy
99 | 70% | 180 | 60 | 168 | 69 | 75
51 | 70% | 90 | 45 | 94.5 | 43.5 | 50
81 | 90% | 120 | 60 | 162 | 81 | 90

## Sheet2
Best Western | 4 | 534.2 | 2 | 311.62 | 30
133.55
Microtel Inn & Suites | 1 | 83.72 |  |  | 30 | 50lb weight limit
Quality Inn | 4 | 451.48 | 2 | 225.74 | 15
112.87

## Flyers
Single Master/Double Sensior/Double Junior
Master Dogs |  | 60
Senior Dogs |  | 30
Junior Dogs |  | 50
Ordered
Flyers for M/Sr/Jr - Flyers in First Series |  |  |  |  | 200
1.1 | Per Bag | Bags | Required At Start | Flyers
Master | 6 | 5 | 30 | 66 | 96
Senior | 6 | 0 | 0 | 33 | 33
Junior | 6 | 1 | 6 | 55 | 61
|  |  |  | 154 | 190
Flyers for M/Sr ONLY - Flyers in First Series |  |  |  |  | 150
1.1 | Per Bag | Bags | Required At Start | Flyers
Master | 6 | 4 | 24 | 66 | 90
Senior | 6 | 0 | 0 | 33 | 33
Junior | 10 | 2 | 20 | 0 | 20
|  |  |  | 99 | 143
Flyers for M/Sr/Jr - Flyers NOT in First Series |  |  |  |  | 450
1.1 | Per Bag | Bags | Required At Start | Flyers
Master | 10 | 7 | 70 | 66 | 136
Senior | 10 | 6 | 60 | 33 | 93
Junior | 10 | 2 | 20 | 55 | 75
|  |  |  | 154 | 304
Flyers for M/Sr ONLY - Flyers NOT in First Series |  |  |  |  | 375
1.1 | Per Bag | Bags | Required At Start | Flyers
Master | 10 | 7 | 70 | 66 | 136
Senior | 10 | 6 | 60 | 33 | 93
Junior | 10 | 4 | 40 | 0 | 40
|  |  |  | 99 | 269

## Ammo
Per Case | 250
| Inventory |  | HT Need | TD Need | Need Total | Delta | Order
25 | Boxes | Rounds |  |  |  |  | Rounds | Cases |  | 6
Poppers | 90 | 2250 | 798 | 4680 | 5478 | -3228 | 3500 | 14 |  | 70 | 420
Ammo | 60 | 1500 | 375 | 1200 | 1575 | -75 | 100 | 0.4
TDs | 12 | Dogs | 60 | Flyers | 40
TD Need | per/Dog | Per/Flyer | Total/TD | Total
Ammo/TD |  | 2.5 | 100 | 1200
Poppers/TD | 6.5 |  | 390 | 4680 | [5 empty] | 150 | 15
2250
2.5 | Poppers Per Series | Callbacks |  |  | Dogs | Poppers Per Dog | Total Poppers | Flyer Ammo (2.5/bird)
|  | 1st Series | 2nd Series | 3rd Series
Master | 3 | 100% | 85% | 75% | 60 | 7.8 | 468 | 150
Senior | 2 | 100% | 75% |  | 40 | 3.5 | 140 | 100
Junior | 2 | 100% | 90% |  | 50 | 3.8 | 190 | 125
[7 empty] | 798 | 375
[7 empty] | 31.92 | 15
5/12 - inventory at June TD 6/4/17 Poppers Kent - 9 Cases and 8 boxes Ammo Kent #7s 2 cases and 8 boxes Remington #6s 2 cases and 5 boxes Federal #6s 1 case and 2 boxes Poppers 9.8 cases - 1 case per TD Ammo 6.5 cases - .4 cases per TD # of TDs Until April HT 12 - 12 Cases of Poppers and 5 cases of Ammo Oct HT

## Judges
Y/N
Roger Everette |  | (410) 398-7081 | rweverett100@gmail.com | 90677
Andrea Fisher | No | (978) 562-2054 | andreajfisher@verizon.net
Christian Ricker | No | (410) 279-0727 |  | 94344
Tony Engrassia | Msg | (252) 904-7272 | tony@wmcnc.com | 95680
Ellison Armfield | No | (336) 941-3207 | armbrooklabs@mac.com | 16929
Rick Vaughan |  | (336) 707-0422 | rvaughan2@gmail.com | 94198
| No | (803) 420-8070 | rb_swift@yahoo.com | Z6124
Macy Swift | No |  | gooddogranch@bellsouth.net | Z7320
Joel Hardy
Judy Gladson | Maybe | (301) 203-1764 | victoryret@aol.com | ZG005
Carol Lewis
Clay Hasty
Sean Rice
Janet Hasty
Joe Romanczak | M | (610) 274-1648 | JTRHunt@aol.com | 95012
Dawn Romanczak | Jr/Sr | (610) 274-1648 | dbrquilt@aol.com | 98940
Doug Hunter | Jr/Sr
Wil Kernodle
George Mcnatt
Kevin Mclaren | M
Cary Irvine
David Hamel
Robert Rascoe
Keith Maready
Monte French
Doug Zahniser
Karen Deman
Rick Shields
Gary Boyce
Robert Johnson |  | (804) 712-3384 | duckhunterrj@aol.com
Shelley Schilling
Betty Dust | Msg | (410) 489-5212 | betty@milltowne.com | 80356
Mario Cilia | Msg | (410) 489-5212 | mario@milltowne.com | 16217